## Task Schedule
Member(s) Assigned | Task Description | Start Date | Stop Date | Total Progression | [10 empty] | January 2018
To This Task |  |  |  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Bryan, Jeff | Planning of Game Requirements/Options | 2017-12-22 | 2017-12-24 | 100% | bar: 22 to 24
Bryan | Coding of GUI Components | 2017-12-26 | 2017-12-28 | 30% | bar: 26 to 28
Jeff, Fardin | Coding of Game State, Win Condition, Board | 2017-12-31 | 2018-01-02 | 20% | bar: January 2018 2 to January 2018 4
Chris | Project Charter | 2018-01-08 | 2018-01-10 | 100% | bar: January 2018 8 to January 2018 10
Jeff, Fardin | Debugging | 2018-01-08 | 2018-01-12 | 100% | bar: January 2018 8 to January 2018 12
Jeff, Fardin | Algorithm | 2018-01-11 | 2018-01-12 | 100% | bar: January 2018 8 to January 2018 12
Bryan, Chris | Planning Phase Document & Gantt Chart | 2018-01-08 | 2018-01-12 | 100% | bar: January 2018 8 to January 2018 12
Jeff, Fardin | Coding of Game State, Win Condition, Board | 2018-01-11 | 2018-01-14 | 100% | bar: January 2018 11 to January 2018 14
Bryan, Fardin | Coding of GUI Components | 2018-01-14 | 2018-01-16 | 60% | bar: January 2018 14 to January 2018 16
Chris | Execution Phase Document | 2018-01-13 | 2018-01-13 | 100% | bar: January 2018 13
Chris | Monitoring/Controlling Phase Document | 2018-01-14 | 2018-01-14 | 100% | bar: January 2018 14
Jeff, Fardin | Coding of GUI Components | 2018-01-13 | 2018-01-15 | 100% | bar: January 2018 13 to January 2018 15
Jeff, Fardin | Testing/Debugging | 2018-01-15 | 2018-01-16 | 100% | bar: January 2018 15 to January 2018 16
Chris, Bryan | Testing | 2018-01-16 | 2018-01-16 | 100% | bar: January 2018 16
Bryan, Jeff, Fardin | Commenting of Code | 2018-01-16 | 2018-01-16 | 100% | bar: January 2018 16
All (Individual) | Closing Document | 2018-01-17 | 2018-01-17 | 100% | bar: January 2018 17